## Expenditure
Date | Phase | Categories | Description | Amount | Payment Status | Vendor | Remarks
2025-02-05 | Plot Purchase | Land Purchase | Land +Other exp | 610000 | Paid |  |  | Total Exp | 1576862
2025-02-23 | Pre-Construction | House Design | Plan | 15500 | Paid
2025-05-06 | Pre-Construction | Pooja Exp | Pooja items | 730 | Paid | Other
2025-05-06 | Pre-Construction | Pooja Exp | Vilakk & others | 4500 | Paid | Other
2025-05-07 | Pre-Construction | Pooja Exp | Kallu & others | 730 | Paid | Other
2025-05-07 | Foundation | Pooja Exp | Murali & helper Cleaning plot | 2300 | Paid | Other
2025-05-08 | Pre-Construction | Pooja Exp | Tea & Snacks | 370 | Paid | Other
2025-05-08 | Pre-Construction | Pooja Exp | murali-Pooja | 1500 | Paid | Other
2025-05-08 | Pre-Construction | Pooja Exp | swamy | 3500 | Paid | Other
2025-05-09 | Foundation | Materials | tree cutting | 1300 | Paid | Other
2025-05-11 | Foundation | Materials | water supply | 1200 | Paid | Other
2025-05-11 | Foundation | Capital | Water tank | 17800 | Paid | Other
2025-05-12 | Foundation | Labour | Murali _Payment | 30000 | Paid | Construction_Cost | Advance_Payment
2025-05-14 | Foundation | Labour | Murali _Payment | 9000 | Paid | Construction_Cost | 5 Workers
2025-05-15 | Foundation | Materials | breakfast | 420 | Paid | Other
2025-05-15 | Foundation | Materials | lunch | 1500 | Paid | Other
2025-05-15 | Foundation | Materials | cement+transportation | 3900 | Paid | Kannat
2025-05-15 | Foundation | Labour | Murali _Payment | 10000 | Paid | Construction_Cost | 9 Workers
2025-05-15 | Foundation | Materials | M Sand & Metal | 18100 | Paid | Antony | 100 feet 1 1/2+m sand+80 feet 1 1/2
2025-05-15 | Foundation | Materials | steel + transportation | 62690 | Paid | Tata
2025-05-16 | Foundation | Materials | covering blk | 240 | Paid | Other
2025-05-16 | Foundation | Materials | water | 250 | Paid | Other
2025-05-16 | Foundation | Labour | Murali _Payment | 3000 | Paid | Construction_Cost | 3 Workers
2025-05-17 | Foundation | Capital | Pump accessories | 2015 | Paid | Balaji
2025-05-17 | Foundation | Capital | Water Pump | 4000 | Paid | Lakshmi
2025-05-17 | Foundation | Labour | Murali _Payment | 9000 | Paid | Construction_Cost | 2 Workers
2025-05-19 | Foundation | Labour | Murali _Payment | 500 | Paid | For Lunch
2025-05-19 | Foundation | Labour | Murali _Payment | 2500 | Paid |  | 3 Workers
2025-05-20 | Foundation | Materials | Winding_Wire | 200 | Paid
2025-05-20 | Foundation | Capital | Pump accessories | 330 | Paid
2025-05-20 | Foundation | Capital | Pump Installation | 700 | Paid
2025-05-20 | Foundation | Labour | Murali _Payment | 3000 | Paid |  | 3 workers
2025-05-21 | Foundation | Materials | Water | 120 | Paid
2025-05-21 | Foundation | Materials | Food | 220 | Paid
2025-05-21 | Foundation | Materials | Lunch | 1540 | Paid |  | 11 Biriyani
2025-05-21 | Foundation | Materials | cement+transportation | 7600 | Paid | 200 for transport
2025-05-21 | Foundation | Labour | Murali _Payment | 10000 | Paid |  | 8 Workers
2025-05-23 | Foundation | Labour | Murali _Payment | 3500 | Paid |  | 3 Workers
2025-05-24 | Foundation | Materials | Water | 120 | Paid |  | 3 Workers
2025-05-24 | Foundation | Materials | Winding_Wire | 175 | Paid
2025-05-24 | Foundation | Labour | Murali _Payment | 500 | Paid |  | 3 Workers
2025-05-24 | Foundation | Labour | Murali _Payment | 5000 | Paid |  | 3 Workers
2025-05-25 | Foundation | Materials | Plate | 40 | Paid
2025-05-25 | Foundation | Materials | breakfast | 276 | Paid
2025-05-25 | Foundation | Materials | Drink - 1Litr MC+peanut | 895 | Paid
2025-05-25 | Foundation | Materials | Water | 1200 | Paid
2025-05-25 | Foundation | Materials | Lunch | 1680 | Paid |  | 8 Workers
2025-05-25 | Foundation | Materials | M_Sand+Cement | 4100 | Paid |  | 3 package cement+
2025-05-25 | Foundation | Materials | Metal | 6000 | Paid |  | Material delivered on 24/05/2025
2025-05-25 | Foundation | Materials | cement+transportation | 9500 | Paid
2025-05-25 | Foundation | Materials | 3/4 Metal -175 Feet | 10500 | Paid | KL43M9901, 7.30 am to 8am | Material delivered on 20/05/2025
2025-05-25 | Foundation | Materials | M Sand - 175 Feet | 11900 | Paid | KL43Q0704, 7.30am to 8am | Material delivered on 20/05/2025
2025-05-25 | Foundation | Labour | Murali _Payment | 20000 | Paid |  | 8 Workers
2025-05-27 | Foundation | Labour | Murali _Payment | 2000 | Paid |  | 2 workers
2025-05-28 | Foundation | Materials | Plastic Sheet | 83 | Paid
2025-05-28 | Foundation | Labour | Murali _Payment | 3500 | Paid
2025-05-29 | Foundation | Labour | Murali _Payment | 5000 | Paid
2025-05-29 | Foundation | Materials | Steel + transportation | 25510 | Paid |  | Transpotation
2025-05-31 | Foundation | Labour | Murali _Payment | 5000 | Paid
2025-05-31 | Foundation | Materials | 3/4 in Metal | 6600 | Paid
2025-06-01 | Foundation | Materials | M Sand 175 feet | 11900 | Paid |  | Material delivered on 26/05/2025
2025-06-01 | Foundation | Materials | Brick 500 Nos | 21250 | Paid |  | Material delivered on 26/05/2025
2025-06-02 | Foundation | Labour | Murali _Payment | 3000 | Paid |  | 3 Workers
2025-06-03 | Foundation | Capital | Tarpolin | 350 | Paid
2025-06-03 | Foundation | Labour | Murali _Payment | 3000 | Paid
2025-06-04 | Foundation | Labour | Murali _Payment | 3000 | Paid
2025-06-05 | Foundation | Materials | Water | 120 | Paid
2025-06-05 | Foundation | Materials | P-sand | 1862 | Paid |  | 22 feet 1562+300
2025-06-05 | Foundation | Materials | Cement | 3160 | Paid
2025-06-05 | Foundation | Labour | Murali _Payment | 10000 | Paid |  | 4 Workers
2025-06-07 | Foundation | Labour | Murali _Payment | 7000 | Paid |  | 4 Workers
2025-06-08 | Foundation | Materials | Kalpodi | 17200 | Paid |  | 4 Load - Material delivered on 10/02/2025
2025-06-10 | Foundation | Labour | Murali _Payment | 1000 | Paid |  | 1 worker
2025-06-11 | Foundation | Labour | Murali _Payment | 6000 | Paid |  | 5 worker
2025-06-12 | Foundation | Labour | Murali _Payment | 10000 | Paid |  | 5 worker
2025-06-12 | Ground Floor & Roofing | Materials | Bicks -500 pieces | 21250 | Paid |  | 1 Load brick- paid dtd 15/6/25
2025-06-13 | Ground Floor & Roofing | Labour | Murali _Payment | 2500 | Paid
2025-06-14 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 1 Worker
2025-06-14 | Ground Floor & Roofing | Materials | Cement | 4000 | Paid
2025-06-15 | Foundation | Materials | Kalpodi | 17200 | Paid |  | 4 Load - Material delivered on 10/06/2025
2025-06-16 | Ground Floor & Roofing | Labour | Murali _Payment | 4500 | Paid |  | 3 Worker
2025-06-17 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 3 Worker
2025-06-18 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 3 Worker
2025-06-19 | Ground Floor & Roofing | Labour | Murali _Payment | 4000 | Paid |  | 4 Worker
2025-06-20 | Ground Floor & Roofing | Labour | Murali _Payment | 4000 | Paid |  | 4 Worker
2025-06-21 | Ground Floor & Roofing | Labour | Murali _Payment | 20000 | Paid |  | 4 Worker
2025-06-21 | Ground Floor & Roofing | Materials | Brick 500 Nos | 21200 | Paid |  | Paid 24.06.2025 (delivered on 16-16-2025)
2025-06-24 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 4 Worker
2025-06-25 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 4 Worker
2025-06-25 | Ground Floor & Roofing | Materials | Brick 500 Nos | 21250 | Paid |  | Paid 29.06.2025
2025-06-26 | Ground Floor & Roofing | Labour | Murali _Payment | 1000 | Paid |  | Paid to Kumar through Gpay
2025-06-28 | Ground Floor & Roofing | Labour | Murali _Payment | 5000 | Paid |  | Paid advance as a Hospital treatment
2025-06-30 | Ground Floor & Roofing | Labour | Murali _Payment | 5000 | Paid |  | Through Phonepay
2025-07-01 | Ground Floor & Roofing | Labour | Murali _Payment | 2000 | Paid |  | Through Phonepay
2025-07-02 | Ground Floor & Roofing | Labour | Murali _Payment | 6600 | Paid |  | 2 person - 600 phonepay
2025-07-03 | Ground Floor & Roofing | Labour | Murali _Payment | 3000 | Paid |  | 3 Worker
2025-07-04 | Ground Floor & Roofing | Labour | Murali _Payment | 5000 | Paid |  | 3 Worker
2025-07-04 | Ground Floor & Roofing | Materials | Steel + transportation | 28140 | Paid |  | Delivered on 07.04.2025
2025-07-04 | Ground Floor & Roofing | Materials | Drinking Water | 120 | Paid
2025-07-05 | Ground Floor & Roofing | Labour | Murali _Payment | 25000 | Paid |  | 6 Workers
2025-07-05 | Ground Floor & Roofing | Materials | Food | 1250 | Paid
2025-07-05 | Ground Floor & Roofing | Materials | Black_Tarpolin | 285 | Paid
2025-07-05 | Ground Floor & Roofing | Materials | Cement | 7000 | Paid
2025-07-05 | Ground Floor & Roofing | Materials | Water | 1200 | Paid
2025-07-05 | Ground Floor & Roofing | Materials | breakfast | 120 | Paid
2025-07-05 | Ground Floor & Roofing | Materials | Msand + Matel | 23300 | Paid | Antony
2025-07-07 | Ground Floor & Roofing | Labour | Murali _Payment | 3500 | Paid
2025-07-08 | Ground Floor & Roofing | Labour | Murali _Payment | 3500 | Paid
2025-07-09 | Ground Floor & Roofing | Labour | Murali _Payment | 8000 | Paid
2025-07-09 | Ground Floor & Roofing | Materials | Drinking Water | 120 | Paid
2025-07-10 | Ground Floor & Roofing | Labour | Murali _Payment | 3500 | Paid
2025-07-10 | Ground Floor & Roofing | Materials | Rope and fense cover | 730 | Paid
2025-07-11 | Ground Floor & Roofing | Labour | Murali _Payment | 4500 | Paid |  | cash
2025-07-11 | Ground Floor & Roofing | Labour | Murali _Payment | 500 | Paid |  | phone pay unni auto
2025-07-12 | Ground Floor & Roofing | Labour | Murali _Payment | 10000 | Paid
2025-07-12 | Electrical | Materials | Electrical_Items | 1962 | Paid
2025-07-12 | Ground Floor & Roofing | Materials | Steel + transportation | 3150 | Paid |  | Tmt steel 8mm (anjaneya) 3150/-
2025-07-13 | Ground Floor & Roofing | Materials | Hardware | 240 | Paid
2025-07-13 | Ground Floor & Roofing | Labour | Murali _Payment | 4000 | Paid
2025-07-14 | Ground Floor & Roofing | Labour | Murali _Payment | 4000 | Paid
2025-07-15 | Ground Floor & Roofing | Labour | Murali _Payment | 4000 | Paid
2025-07-15 | Ground Floor & Roofing | Materials | Steel + transportation | 3640 | Paid
2025-07-15 | Ground Floor & Roofing | Materials | Drinking Water | 120 | Paid
2025-07-16 | Ground Floor & Roofing | Labour | Murali _Payment | 2500 | Paid
2025-07-16 | Electrical | Labour | Electritian | 1000 | Paid
2025-07-17 | Ground Floor & Roofing | Labour | Murali _Payment | 30000 | Paid
2025-07-17 | Ground Floor & Roofing | Materials | Cement | 2100 | Paid
2025-07-17 | Ground Floor & Roofing | Materials | Cement | 2100 | Paid
2025-07-17 | Ground Floor & Roofing | Materials | Cement | 9450 | Paid
2025-07-17 | Ground Floor & Roofing | Materials | Lunch | 2080 | Paid
2025-07-17 | Ground Floor & Roofing | Materials | breakfast | 314 | Paid
2025-07-27 | 1st Floor & Roofing | Labour | Murali _Payment | 1000 | Paid |  | Fund Transfered to Kumar
2025-07-28 | 1st Floor & Roofing | Labour | Murali _Payment | 3000 | Paid
2025-07-27 | 1st Floor & Roofing | Materials | Brick | 26500 | Paid |  | Antony
2025-07-29 | 1st Floor & Roofing | Labour | Murali _Payment | 2000 | Paid
2025-07-30 | 1st Floor & Roofing | Labour | Murali _Payment | 2000 | Paid
2025-08-02 | 1st Floor & Roofing | Labour | Murali _Payment | 6000 | Paid
2025-07-29 | 1st Floor & Roofing | Materials | Cement | 3800 | Paid
2025-08-03 | 1st Floor & Roofing | Materials | Brick | 27175 | Paid |  | paid_to antony
2025-08-04 | 1st Floor & Roofing | Materials | Steel + transportation | 50840 | Paid
2025-08-04 | 1st Floor & Roofing | Labour | Murali _Payment | 5000 | Paid
2025-08-05 | 1st Floor & Roofing | Labour | Murali _Payment | 3000 | Paid
2025-08-05 | 1st Floor & Roofing | Materials | Water | 1200 | Paid
2025-08-06 | 1st Floor & Roofing | Labour | Murali _Payment | 4000 | Paid
2025-08-07 | 1st Floor & Roofing | Labour | Murali _Payment | 2000 | Paid
2025-08-08 | 1st Floor & Roofing | Labour | Murali _Payment | 2000 | Paid
2025-08-07 | 1st Floor & Roofing | Materials | Brick | 21250 | Pending

## Loan
Date | Phase | Categories | Description | Amount | Payment Status | Vendor | Remarks
2025-02-05 | Plot Purchase | Plot purchase | Cash_Credited at Bank | 1322260 | Credited | BOB
2025-05-05 | Foundation | Installment | Cash_Credited at Bank | 500000 | Credited | BOB
2025-06-23 | Ground Floor & Roofing | Installment | Cash_Credited at Bank | 400000 | Credited | BOB
2025-06-23 | 1st Floor & Roofing | Installment | Cash_Credited at Bank | 450000 | Credited | BOB

## Estimation
Phase No | Phase Name | Categories | Transaction_Type | Estimated Start Date | Estimated End Date | Estimated Cost | Status | Photos
1 | Pre-Construction Phase | Pre-Construction | House Plan and Site Cleaning | 2025-05-06 | 2025-05-08 | 25000 | Completed
2 | Construction Phase | Foundation | Site Preparation¦ Laying the Foundation of the Building ¦ Laying Plinth Beam and Slab | 2025-05-09 | 2025-05-25 | 450000 | Completed | Foundation2.jpg
3 | Construction Phase | Ground Floor & Roofing | Structure | 2025-05-26 | 2025-07-23 | 325000 | Completed
4 | Construction Phase | 1st Floor & Roofing | Structure | 2025-07-27 | 2025-08-15 | 275000 | In progress
5 | Construction Phase | Electrical | Electrical Wiring | 2025-07-16 | 2025-09-22 | 115000 | In progress
6 | Construction Phase | Plumbing | Plumbing & Drainage | 2025-08-15 | 2025-09-22 | 125000 | Yet to start
7 | Construction Phase | Plastering & Fixtures | Plastered with a wall finish | 2025-09-04 | 2025-09-23 | 100000 | Yet to start
8 | Construction Phase | Windows and doors | windows and doors | 2025-08-15 | 2025-09-22 | 125000 | Yet to start
9 | Construction Phase | Flooring & Tiling | Flooring Work /Lay Tile | 2025-08-15 | 2025-08-30 | 130000 | Yet to start
10 | Construction Phase | Interior | Interior and Exterior Design Work | 2025-10-01 | 2025-10-07 | 350000 | Yet to start
11 | Construction Phase | Exterior | Painting Work | 2025-09-23 | 2025-10-01 | 150000 | Yet to start
12 | Post-Construction Phase | Misc expenses | Carporch+SeideWall(WholePlastering)+Gate+outside floor Tilling+plasting Water tank+Septik Tank+Water tank re alignment | 2025-10-01 | 2025-10-07 | 160000 | Yet to start

## Copy of Estimation (hidden)
Phase No | Phase Name | Categories | Transaction_Type | Estimated Cost | Estimated End | Estimated Cost | Status
1 | House Design and Plan | Design & Plan | House Plan | 2025-03-10 | 2025-05-23 | 20000 | Completed
2 | Pre-Construction Phase | Foundation | Tree Cutting | 2025-05-09 | 2025-05-09 | 24000 | Completed
3 | Pre-Construction Phase | Foundation | Pooja & Other exp | 2025-05-04 | 2025-05-06 | 15000 | Completed
4 | Pre-Construction Phase | Foundation | Site Cleaning | 2025-05-06 | 2025-05-08 | 5000 | Completed
5 | Construction Phase | Foundation | Site Preparation | 2025-05-10 | 2025-05-12 | 10000 | Completed
6 | Construction Phase | Foundation | Laying the Foundation of the Building | 2025-05-14 | 2025-05-19 | 150000 | Completed
7 | Construction Phase | Foundation | Laying Plinth Beam and Slab | 2025-05-19 | 2025-05-25 | 75000 | Ongoing
8 | Construction Phase | Brickwork | Column and Beam/wall | 2025-05-26 | 2025-06-15 | 293000 | Ongoing
9 | Construction Phase | Brickwork | Masonry Work and staire case | 2025-06-16 | 2025-07-23 | 315000 | Ongoing
10 | Construction Phase | Roofing | Lintle and Roof | 2025-08-16 | 2025-09-10 | 250000 | Ongoing
11 | Construction Phase | Electrical | Electrical Wiring | 2025-09-10 | 2025-09-22 | 90000 | Ongoing
12 | Construction Phase | Electrical | Plumbing & Drainage | 2025-09-22 | 2025-10-04 | 110000 | Ongoing
13 | Construction Phase | Plastering & Fixtures | Plastered with a wall finish | 2025-10-04 | 2025-11-04 | 125000 | Ongoing
14 | Construction Phase | Windows and doors | windows and doors | 2025-11-04 | 2025-11-20 | 175000 | Ongoing
15 | Construction Phase | Flooring & Tiling | Flooring Work /Lay Tile | 2025-11-20 | 2025-11-30 | 175000 | Ongoing
16 | Post-Construction Phase | Interior | Interior and Exterior Design Work | 2025-11-30 | 2025-12-01 | 350000 | Ongoing
17 | Post-Construction Phase | Exterior | Painting Work | 2025-12-01 | 2025-12-14 | 127000 | Ongoing
18 | Post-Construction Phase | Post-Construction | Quality Checks | 2025-12-14 | 2025-12-20 | 25000 | Ongoing